## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Jagruthi Buchala | 17-Sep-2026 | Embedding generation needed safe handling for empty input and consistent vector normalization. | Sprint 1 | Jagruthi Buchala | Logical | Added empty-input handling and normalized embedding output in embed_chunks(). | 17-Sep-2026 | Closed | Embedding validation passed.
2 | Jagruthi Buchala | 17-Sep-2026 | Semantic similarity alone could rank chunks poorly when exact query terms were important. | Sprint 2 | Jagruthi Buchala | Logical | Added keyword-overlap and exact-term scoring to the reranking pipeline. | 17-Sep-2026 | Closed | Ranking re-tested with representative queries.
3 | Jagruthi Buchala | 17-Sep-2026 | Candidate retrieval could contain low-relevance or duplicate chunks before final context selection. | Sprint 2 | Jagruthi Buchala | Logical | Added relevance-threshold filtering and safe deduplication. | 17-Sep-2026 | Closed | Duplicate and low-score cases validated.
4 | Jagruthi Buchala | 17-Sep-2026 | Completeness/list queries could lose related chunks that belonged to the same logical section. | Sprint 2 | Jagruthi Buchala | Functional | Added section-aware context expansion for related chunks. | 17-Sep-2026 | Closed | Completeness and list-query tests passed.
5 | Jagruthi Buchala | 17-Sep-2026 | Refined clarification queries could be passed through conversational rewriting again. | Sprint 3 | Jagruthi Buchala | Logical | Skipped memory rewriting when refined_query was already available. | 17-Sep-2026 | Closed | Clarification-to-retrieval flow regression passed.
6 | Jagruthi Buchala | 17-Sep-2026 | Document-internal citations such as [7, 8] could be mistaken for retrieved RAG source labels. | Sprint 3 | Jagruthi Buchala | Functional | Updated response-generation instructions so only retrieved-context labels are treated as source citations. | 17-Sep-2026 | Closed | Source panel and answer citation display re-tested.
7 | Jagruthi Buchala | 17-Sep-2026 | Knowledge-base content was initially not isolated by user after multi-user support was introduced. | Sprint 4 | Jagruthi Buchala | Data Isolation | Associated uploaded documents and indexed content with individual users. | 17-Sep-2026 | Closed | User-specific retrieval and data isolation validated.
8 | Jagruthi Buchala | 17-Sep-2026 | Analytics integration required backend and frontend changes to agree on PostgreSQL-backed data and theme outputs. | Sprint 4 | Jagruthi Buchala | Integration | Updated database configuration/data access and connected Query Analytics/Knowledge Gap APIs to the UI. | 17-Sep-2026 | Closed | End-to-end analytics workflow validated.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others