## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload knowledge-base documents so that I can query their content. | Must | Document extraction pipeline | Team | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want documents in supported formats to be extracted and normalized for retrieval. | Must | Document upload | Team | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want document text split into meaningful chunks so retrieval can find relevant context. | Must | Extraction/cleaning | Team | Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want semantic embeddings stored in a vector database for knowledge retrieval. | Must | Chunking | Team | Completed
Sprint 1 | Sprint 1 | H-US-01 | As a user, I want document chunks converted into reliable vector embeddings so knowledge can be searched semantically. | Must | Embedding | Jagruthi Buchala | Completed
Sprint 2 | Sprint 2 | US-05 | As a user, I want my question understood before retrieval so relevant knowledge is searched. | Must | RAG pipeline | Team | Completed
Sprint 2 | Sprint 2 | US-06 | As a user, I want queries routed appropriately between retrieval, clarification and direct response paths. | Must | Query understanding | Team | Completed
Sprint 2 | Sprint 2 | US-07 | As a user, I want retrieved chunks reranked so the most relevant evidence is used. | Must | Reranker | Jagruthi Buchala | Completed
Sprint 2 | Sprint 2 | US-08 | As a user, I want answers grounded in uploaded documents with source information. | Must | Response generation | Team | Completed
Sprint 2 | Sprint 2 | H-US-02 | As a user, I want retrieved chunks ranked using semantic, keyword and exact-match signals so the most relevant evidence is selected. | Must | Vector retrieval | Jagruthi Buchala | Completed
Sprint 2 | Sprint 2 | H-US-03 | As a user, I want low-relevance and duplicate chunks filtered and the best context assembled before answer generation. | Must | Candidate retrieval | Jagruthi Buchala | Completed
Sprint 3 | Sprint 3 | US-09 | As a user, I want follow-up questions to retain conversation context. | Must | Conversation ID/memory | Team | Completed
Sprint 3 | Sprint 3 | US-10 | As a user, I want clarification questions when my query is ambiguous or incomplete. | Must | Query understanding | Team | Completed
Sprint 3 | Sprint 3 | US-11 | As a user, I want voice input and spoken responses for easier interaction. | Should | Browser Speech APIs | Team | Completed
Sprint 3 | Sprint 3 | US-12 | As a user, I want to inspect sources, chunks, relevance and citations behind an answer. | Must | Retrieval metadata | Team | Completed
Sprint 3 | Sprint 3 | H-US-04 | As a user, I want follow-up queries to retain conversation state and be routed correctly between retrieval and clarification paths. | Must | Conversation state | Jagruthi Buchala | Completed
Sprint 3 | Sprint 3 | H-US-05 | As a system, I want agent outputs validated so multi-agent workflow state remains consistent during clarification and retrieval. | Must | Agent state and routing | Jagruthi Buchala | Completed
Sprint 4 | Sprint 4 | US-13 | As a user, I want to view query history and conversation statistics. | Should | Conversation API | Team | Completed
Sprint 4 | Sprint 4 | US-14 | As a user, I want charts for query activity, conversation usage and confidence distribution. | Should | History dashboard | Team | Completed
Sprint 4 | Sprint 4 | US-15 | As an administrator, I want analytics and knowledge-gap information to understand unanswered or low-confidence queries. | Should | Analytics service | Team | Completed
Sprint 4 | Sprint 4 | H-US-06 | As an analyst, I want semantically related user queries grouped into common themes so analytics and knowledge-gap detection can identify recurring needs. | Should | Query analytics | Jagruthi Buchala | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1–4 BACKLOG — HARSHIT BISHT
US-01 | US-01-T01 | Set up Sentence Transformers embedding module and select all-MiniLM-L6-v2 | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | US-01-T02 | Implement embed_chunks with empty-input handling and normalized vectors | TBD | TBD | Jagruthi Buchala | Development | Completed | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | US-01-T03 | Validate embedding dimensions and vector-length consistency | TBD | TBD | Jagruthi Buchala | Testing | Completed | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | US-01-T04 | Integrate embeddings with document indexing and vector-store flow | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | US-01-T05 | Connect frontend query flow with the FastAPI retrieval pipeline and verify responses | TBD | TBD | Jagruthi Buchala | Development | Completed | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | US-01-T06 | Run end-to-end embedding integration testing and demo validation | TBD | TBD | Jagruthi Buchala | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | US-02-T01 | Define query-aware reranking with semantic similarity as the primary signal | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | US-02-T02 | Add keyword-overlap and exact-term scoring to candidate ranking | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | US-02-T03 | Add evidence and synergy scoring for entity-plus-attribute queries | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | US-03-T01 | Implement relevance-threshold filtering and safe deduplication | TBD | TBD | Jagruthi Buchala | Development | Completed | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | US-02-T04 | Integrate reranker.py into Retrieval Agent and merge semantic/exact candidates | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | US-03-T02 | Add completeness/list-query handling and section-aware context expansion | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | US-03-T03 | Test retrieval quality, top-K output and adjust relevance behavior | TBD | TBD | Jagruthi Buchala | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | US-04-T01 | Extend workflow state with conversation ID, memory and clarification fields | TBD | TBD | Jagruthi Buchala | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | US-04-T02 | Implement deterministic routing for factual, procedural, comparative and ambiguous queries | TBD | TBD | Jagruthi Buchala | Development | Completed | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | US-04-T03 | Update workflow nodes for memory context, follow-up resolution and clarification | TBD | TBD | Jagruthi Buchala | Development | Completed | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | US-04-T04 | Integrate previous-turn context and convert follow-ups into standalone queries | TBD | TBD | Jagruthi Buchala | Development | Completed | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | US-04-T05 | Prevent duplicate conversational rewriting when refined_query already exists | TBD | TBD | Jagruthi Buchala | Testing | Completed | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | US-04-T06 | Run end-to-end clarification → refinement → retrieval → response testing | TBD | TBD | Jagruthi Buchala | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | US-05-T01 | Correct document-internal citation labels being mistaken for RAG source labels | TBD | TBD | Jagruthi Buchala | Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | US-05-T02 | Validate source visibility and voice behavior while preserving on-screen citations | TBD | TBD | Jagruthi Buchala | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | US-06-T01 | Migrate application database from MySQL to PostgreSQL and update data-access configuration | TBD | TBD | Jagruthi Buchala | Development | Completed | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | US-06-T02 | Implement semantic common-query theme detection using Sentence Transformers | TBD | TBD | Jagruthi Buchala | AI/RAG | Completed | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | US-06-T03 | Associate knowledge-base documents and indexed content with individual users | TBD | TBD | Jagruthi Buchala | Development | Completed | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | US-06-T04 | Integrate Query Analytics and Knowledge Gap frontend/backend flows and APIs | TBD | TBD | Jagruthi Buchala | Development | Completed | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | US-06-T05 | Validate migration, theme analysis, user isolation and analytics integration end-to-end | TBD | TBD | Jagruthi Buchala | Testing | Completed | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Embedding model choice and vector representation needed validation. | Selected all-MiniLM-L6-v2 and defined the embedding module around normalized vectors.
Sprint 1 | Day 4 | Embedding pipeline had to connect cleanly with document indexing. | Integrated embeddings into the indexing/vector-store flow and validated query access.
Sprint 2 | Day 2 | Semantic similarity alone was not enough for exact query terms. | Added keyword-overlap and exact-term scoring to improve candidate ordering.
Sprint 2 | Day 5 | Candidate results needed consistent merging and duplicate control. | Integrated the reranker and added relevance filtering plus safe deduplication.
Sprint 3 | Day 2 | Routing needed to distinguish normal and ambiguous queries deterministically. | Updated query routing while preserving existing retrieval behavior.
Sprint 3 | Day 5 | Refined queries were being rewritten again during conversational processing. | Skipped memory rewriting when refined_query was already present.
Sprint 3 | Day 7 | Document-internal citation labels could conflict with RAG source labels. | Restricted source-label interpretation to retrieved-context citation markers.
Sprint 4 | Day 2 | Analytics needed semantic grouping of related queries. | Added Sentence Transformer based common-query theme detection.
Sprint 4 | Day 3 | Knowledge-base documents needed user-level isolation after database migration. | Associated uploaded/indexed content with individual users.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | TBD | TBD | Jagruthi Buchala | Start embedding validation earlier | Stop waiting until end-to-end integration to validate vector shape | Continue using explicit model and vector validation | Added empty-input handling, normalization and embedding-dimension checks before integration.
2 | Sprint 2 | TBD | TBD | Jagruthi Buchala | Start testing ranking signals with representative query types | Stop relying on semantic similarity alone | Continue validating top-K relevance and context quality | Added keyword, exact-match, evidence and synergy signals plus filtering/deduplication.
3 | Sprint 3 | TBD | TBD | Jagruthi Buchala | Start state-transition testing before full workflow tests | Stop allowing refined queries to be rewritten twice | Continue preserving existing M2 state while extending M3 routing | Extended shared state, corrected routing and validated clarification/memory flows end-to-end.
4 | Sprint 4 | TBD | TBD | Jagruthi Buchala | Start data-isolation and migration checks alongside analytics work | Stop treating analytics data as globally interchangeable across users | Continue end-to-end regression after backend/frontend changes | Migrated to PostgreSQL, added semantic themes, user-specific KB support and analytics integration validation.